## Sheet1
Task Name | Expected Duration | Start Date | End Date | 4th Sep | 5th Sep | 6th Sep | 7th Sep | 8th Sep | 9th Sep | 10th Sep | 11th Sep | 12th Sep | 13th Sep | 14th Sep | 15th Sep | 16th Sep | 17th Sep | 18th Sep | 19th Sep | 20th Sep | 21st Sep | 22nd Sep | 23rd Sep | 24th Sep | 25th Sep | 26th Sep | 27th Sep | 28th Sep | 29th Sep | 30th Sep | 1st Oct | 2nd Oct | 3rd Oct | 4th Oct | 5th Oct | 6th Oct | 7th Oct | 8th Oct | 9th Oct | 10th Oct | 11th Oct | 12th Oct | 13th Oct | 14th Oct | 15th Oct | 16th Oct | 17th Oct | 18th Oct | 19th Oct | 20th Oct | 21st Oct | 22nd Oct | 23rd Oct | 24th Oct | 25th Oct | 26th Oct | 27th Oct | 28th Oct | 29th Oct | 30th Oct | 31st Oct | 1st Nov | 2nd Nov | 3rd Nov
Weekly Review | 1 day
Assembly and Planning | 5-10 days | 4th Sep | 15th Sep
Team formation | 1-3 days | 4th Sep | 6th Sep
Identifying lifecyle, model | 1 week | 6th Sep | 12th Sep
Scheduling | 1-3 days | 12th Sep | 14th Sep
Architecture and Design | 2 Weeks | 16th Sep | 29th Sep | [12 empty] | UI Design | [5 empty] | Finance Systems research
Propose Style | 1 Week | 16th Sep | 23rd Sep
Adopt coding practices | 1 Week | 23rd Sep | 29th Sep
Coding | 2 Weeks | 29th Sep | 13th Oct | [26 empty] | DB Management | [5 empty] | Finance Systems
Exploring CM | 1 Week | 29th Sep | 6th Oct
Coding/Implementation | 1 Week | 6th Oct | 13th Oct
[44 empty] | Testing | [5 empty] | Finance Testing
Testing | 2 Weeks | 13th Oct | 27th Oct
Preparing Strategy | 1 Week | 13th Oct | 20th Oct
Testing | 1 Week | 20th Oct | 27th Oct
Publishing | 1 Week | 27th Oct | 3rd Nov
Presentation and Report | 1 Week | 27th Oct | 3rd Nov